## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 02. Vehicle Search | 2.02 | Compare Vehicles | Search for Proper UI Design | N | 2024-10-30 | 2024-10-30 | 100% | Tarjanee Desai
2 | 02. Vehicle Search | 2.02 | Compare Vehicles | Define Comparison Criteria for Selected Features | Y | 2024-10-30 | 2024-10-31 | 100% | Tarjanee Desai
3 | 02. Vehicle Search | 2.02 | Compare Vehicles | Implement Core Comparison Functionality | N | 2024-10-30 | 2024-10-31 | 100% | Jitendra Rawat
4 | 02. Vehicle Search | 2.02 | Compare Vehicles | Implement API Endpoints | N | 2024-10-30 | 2024-10-31 | 100% | Jitendra Rawat
5 | 02. Vehicle Search | 2.02 | Compare Vehicles | Implement GUI Elements for Feature Comparison | N | 2024-10-30 | 2024-11-03 | 100% | Charitha Gangaraju
6 | 02. Vehicle Search | 2.02 | Compare Vehicles | Highlight Feature Differences Based on Comparison Results | N | 2024-10-30 | 2024-11-01 | 100% | Charitha Gangaraju
7 | 02. Vehicle Search | 2.02 | Compare Vehicles | Implement Calculations Based on Provided Information | N | 2024-10-30 | 2024-11-01 | 100% | Charitha Gangaraju
8 | 02. Vehicle Search | 2.02 | Compare Vehicles | Perform Exploratory Testing on Comparison Functionality | N | 2024-11-02 | 2024-11-03 | 100% | Krupali Dangshiya
9 | 02. Vehicle Search | 2.02 | Compare Vehicles | Validate Display and Accuracy of Feature Differences | N | 2024-11-02 | 2024-11-03 | 100% | Harsh Patel
10 | 02. Vehicle Search | 2.02 | Compare Vehicles | Verify Calculation Accuracy for Comparison Data | N | 2024-11-02 | 2024-11-03 | 100% | Krupali Dangshiya
11 | 02. Vehicle Search | 2.03 | Filter Vehicles | Search for Proper UI Design | N | 2024-10-30 | 2024-10-30 | 100% | Tarjanee Desai
12 | 02. Vehicle Search | 2.03 | Filter Vehicles | Implement API for Filter Data Retrieval | N | 2024-10-31 | 2024-10-31 | 100% | Jitendra Rawat
13 | 02. Vehicle Search | 2.03 | Filter Vehicles | Implement Core Filtering Functionality | N | 2024-10-31 | 2024-10-31 | 100% | Jitendra Rawat
14 | 02. Vehicle Search | 2.03 | Filter Vehicles | Implement GUI for Filter Options and Results Display | N | 2024-10-31 | 2024-11-01 | 100% | Jitendra Rawat
15 | 02. Vehicle Search | 2.03 | Filter Vehicles | Define Filter Criteria | Y | 2024-10-30 | 2024-10-30 | 100% | Tarjanee Desai
16 | 02. Vehicle Search | 2.03 | Filter Vehicles | Perform Exploratory Testing | N | 2024-10-31 | 2024-11-01 | 100% | Avinash Bhavancheekar
17 | 02. Vehicle Search | 2.03 | Filter Vehicles | Implement Make Filter with Dynamic Options | N | 2024-10-31 | 2024-11-01 | 100% | Jitendra Rawat
18 | 02. Vehicle Search | 2.03 | Filter Vehicles | Implement Field Validation for Filter Inputs | N | 2024-10-31 | 2024-11-01 | 100% | Jitendra Rawat
19 | 02. Vehicle Search | 2.03 | Filter Vehicles | Create Multi-Select Filter Options | N | 2024-10-31 | 2024-11-02 | 100% | Jitendra Rawat
20 | 02. Vehicle Search | 2.03 | Filter Vehicles | Display Real-Time Availability Status | N | 2024-10-31 | 2024-11-02 | 100% | Jitendra Rawat
21 | 02. Vehicle Search | 2.03 | Filter Vehicles | Implement Filter based on Price Range | N | 2024-10-31 | 2024-11-01 | 100% | Jitendra Rawat
22 | 02. Vehicle Search | 2.03 | Filter Vehicles | Implement Model Filter Dependent on Selected Make | N | 2024-10-31 | 2024-11-01 | 100% | Jitendra Rawat
23 | 02. Vehicle Search | 2.03 | Filter Vehicles | Perform Exploratory Testing on Filter Functionality | N | 2024-10-31 | 2024-11-01 | 100% | Jitendra Rawat
24 | 02. Vehicle Search | 2.03 | Filter Vehicles | Verify Field Validation for Filter Inputs | N | 2024-11-02 | 2024-11-03 | 100% | Avinash Bhavancheekar
25 | 02. Vehicle Search | 2.03 | Filter Vehicles | Test Real-Time Availability Status Display | N | 2024-11-02 | 2024-11-03 | 100% | Avinash Bhavancheekar
26 | 02. Vehicle Search | 2.03 | Filter Vehicles | Test Dependent Model Filter Based on Make Selection | N | 2024-11-02 | 2024-11-03 | 100% | Avinash Bhavancheekar
27 | 03. Booking Management | 3.01 | Book Vehicles | Search for Proper UI Design | N | 2024-11-06 | 2024-11-06 | 100% | Harsh Patel
28 | 03. Booking Management | 3.01 | Book Vehicles | Implement API for Booking Data Submission and Retrieval | N | 2024-11-06 | 2024-11-09 | 100% | Jitendra Rawat
29 | 03. Booking Management | 3.01 | Book Vehicles | Implement Logic to Retrieve User’s Most Recent Pickup Location | Y | 2024-11-06 | 2024-11-09 | 100% | Bhavin Goswami
30 | 03. Booking Management | 3.01 | Book Vehicles | Implement Logic to Pre-fill Booking Form with User’s General Information | Y | 2024-11-06 | 2024-11-09 | 100% | Bhavin Goswami
31 | 03. Booking Management | 3.01 | Book Vehicles | Send a Email Confirmation as soon as the Booking is successful | N | 2024-11-06 | 2024-11-09 | 100% | Bhavin Goswami
32 | 03. Booking Management | 3.01 | Book Vehicles | Calculate applicable taxes and fees based on the rental location and vehicle type | N | 2024-11-06 | 2024-11-08 | 100% | Bhavin Goswami
33 | 03. Booking Management | 3.01 | Book Vehicles | Implement GUI for Booking Form and Summary Page | N | 2024-11-06 | 2024-11-08 | 100% | Prithvi Karkera
34 | 03. Booking Management | 3.01 | Book Vehicles | Implement validation on fields to ensure accurate modifications: Past date is not valid | N | 2024-11-06 | 2024-11-08 | 100% | Prithvi Karkera
35 | 03. Booking Management | 3.01 | Book Vehicles | Implement validation on the entitlement code field to ensure it is not blank or null | N | 2024-11-06 | 2024-11-08 | 100% | Prithvi Karkera
36 | 03. Booking Management | 3.01 | Book Vehicles | Mark mandatory fields such as Last Name, Email, and Payment Information | N | 2024-11-06 | 2024-11-08 | 100% | Prithvi Karkera
37 | 03. Booking Management | 3.01 | Book Vehicles | Implement validation on fields to ensure accurate modifications: Last Name is required and not null/blank | N | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
38 | 03. Booking Management | 3.01 | Book Vehicles | Implement validation on fields to ensure accurate modifications: Email field follows the correct format (e.g., user@domain.com) | N | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
39 | 03. Booking Management | 3.01 | Book Vehicles | Implement validation on fields to ensure accurate modifications: Credit card number with valid length and format or not | N | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
40 | 03. Booking Management | 3.01 | Book Vehicles | Implement validation on fields to ensure accurate modifications: Users cannot select a vehicle if it’s already booked for the selected date. | N | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
41 | 03. Booking Management | 3.01 | Book Vehicles | Validate the fields: which is mentioned in previous tasks are implemented | N | 2024-11-14 | 2024-11-17 | 100% | Chandraharsha Kosuri
42 | 03. Booking Management | 3.01 | Book Vehicles | Prevent multiple users from booking the same vehicle simultaneously by locking the vehicle record during the booking transaction. | Y | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
43 | 03. Booking Management | 3.01 | Book Vehicles | Monitor and log connectivity status to external APIs to detect issues | N | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
44 | 03. Booking Management | 3.01 | Book Vehicles | Display Confirmation Message upon Successful Booking | N | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
45 | 03. Booking Management | 3.01 | Book Vehicles | Generate and Display Booking Confirmation Summary | Y | 2024-11-06 | 2024-11-09 | 100% | Prithvi Karkera
46 | 03. Booking Management | 3.01 | Book Vehicles | Implement try-catch blocks: Error should be captured and displayed to business user if unable to complete and process submission. | N | 2024-11-06 | 2024-11-09 | 100% | Bhavin Goswami
47 | 03. Booking Management | 3.01 | Book Vehicles | Implement access controls to restrict who can view or modify personal data in system | N | 2024-11-06 | 2024-11-09 | 100% | Bhavin Goswami
48 | 03. Booking Management | 3.01 | Book Vehicles | Conduct exploratory testing on the vehicle booking process to identify defects and issues | N | 2024-11-14 | 2024-11-17 | 100% | Chandraharsha Kosuri
49 | 03. Booking Management | 3.02 | Send Booking Reminder | Define an Email Format for a Booking Reminder | Y | 2024-11-13 | 2024-11-14 | 100% | Tarjanee Desai
50 | 03. Booking Management | 3.02 | Send Booking Reminder | Implement API for Sending Reminder Notifications | N | 2024-11-13 | 2024-11-14 | 100% | Harsh Patel
51 | 03. Booking Management | 3.02 | Send Booking Reminder | Define Reminder Criteria (e.g., timing, frequency) | Y | 2024-11-13 | 2024-11-13 | 100% | Tarjanee Desai
52 | 03. Booking Management | 3.02 | Send Booking Reminder | Implement Logic to Schedule Reminders Based on Booking Date | N | 2024-11-13 | 2024-11-14 | 100% | Harsh Patel
53 | 03. Booking Management | 3.02 | Send Booking Reminder | Implement access controls to restrict who can schedule the reminders from the system | N | 2024-11-13 | 2024-11-15 | 100% | Harsh Patel
54 | 03. Booking Management | 3.02 | Send Booking Reminder | Perform Exploratory Testing on Reminder Functionality | N | 2024-11-15 | 2024-11-16 | 100% | Sameera Shaik
55 | 03. Booking Management | 3.02 | Send Booking Reminder | Implement Error Handling for Reminder Failures | N | 2024-11-13 | 2024-11-15 | 100% | Bhavin Goswami
56 | 03. Booking Management | 3.04 | View Bookings | Search for Proper UI Design for Booking Overview | N | 2024-11-13 | 2024-11-13 | 100% | Tarjanee Desai
57 | 03. Booking Management | 3.04 | View Bookings | Implement API for Retrieving User Booking History | N | 2024-11-13 | 2024-11-15 | 100% | Jitendra Rawat
58 | 03. Booking Management | 3.04 | View Bookings | Implement Logic to Filter Bookings by Date and Status | N | 2024-11-13 | 2024-11-15 | 100% | Jitendra Rawat
59 | 03. Booking Management | 3.04 | View Bookings | Implement GUI for Displaying Booking Details | N | 2024-11-13 | 2024-11-15 | 100% | Jitendra Rawat
60 | 03. Booking Management | 3.04 | View Bookings | Implement Pagination for Large Booking Lists | N | 2024-11-13 | 2024-11-17 | 100% | Tarjanee Desai
61 | 03. Booking Management | 3.04 | View Bookings | Implement Sort Options for Booking Data | N | 2024-11-13 | 2024-11-16 | 100% | Tarjanee Desai
62 | 03. Booking Management | 3.04 | View Bookings | Implement Search/Filter Functionality for Specific Bookings | N | 2024-11-13 | 2024-11-16 | 100% | Jitendra Rawat
63 | 03. Booking Management | 3.04 | View Bookings | Implement Option to Manage Upcoming Bookings | Y | 2024-11-13 | 2024-11-16 | 100% | Harsh Patel
64 | 03. Booking Management | 3.04 | View Bookings | Implement Option to View Individual Booking | Y | 2024-11-13 | 2024-11-16 | 100% | Prithvi Karkera
65 | 03. Booking Management | 3.04 | View Bookings | Validate Displayed Booking Information for Accuracy | N | 2024-11-15 | 2024-11-18 | 100% | Krupali Dangshiya
66 | 03. Booking Management | 3.04 | View Bookings | Perform Exploratory Testing on Viewing Functionality | N | 2024-11-15 | 2024-11-18 | 100% | Sameera Shaik

## S3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 03. Booking Management | 3.03 | Manage Bookings | Search for Proper UI Design | N | 2024-11-20 | 2024-11-22 | 100% | Tarjanee Desai
2 | 03. Booking Management | 3.03 | Manage Bookings | Design UI to Dynamically Display Editable and Cancellable Bookings | Y | 2024-11-20 | 2024-11-23 | 100% | Tarjanee Desai
3 | 03. Booking Management | 3.03 | Manage Bookings | Define Logic to handle Booking Edits and Cancellations | Y | 2024-11-20 | 2024-11-22 | 100% | Tarjanee Desai
4 | 03. Booking Management | 3.03 | Manage Bookings | Build API to Process Booking Edits with Dependency Checks | N | 2024-11-21 | 2024-11-26 | 100% | Jitendra Rawat
5 | 03. Booking Management | 3.03 | Manage Bookings | Build API to Handle Booking Cancellations and Update Status | N | 2024-11-21 | 2024-11-26 | 100% | Jitendra Rawat
6 | 03. Booking Management | 3.03 | Manage Bookings | Implement Validation for Editable Booking Fields | N | 2024-11-21 | 2024-11-26 | 100% | Charitha Gangaraju
7 | 03. Booking Management | 3.03 | Manage Bookings | Validate Booking Modification Scenarios for Consistency | N | 2024-11-21 | 2024-11-26 | 100% | Tarjanee Desai
8 | 03. Booking Management | 3.03 | Manage Bookings | Add validations and error handling for handling bookings | N | 2024-11-21 | 2024-11-26 | 100% | Harsh Patel
9 | 03. Booking Management | 3.03 | Manage Bookings | Implement Calculations for Booking Edits | N | 2024-11-21 | 2024-11-26 | 100% | Charitha Gangaraju
10 | 03. Booking Management | 3.03 | Manage Bookings | Produce Test Design Specification | N | 2024-12-04 | 2024-12-08 | 100% | Avinash Bhavancheekar
11 | 03. Booking Management | 3.03 | Manage Bookings | Produce Test Case Specification | N | 2024-12-04 | 2024-12-08 | 100% | Tarjanee Desai
12 | 03. Booking Management | 3.03 | Manage Bookings | Perform Testing | N | 2024-11-28 | 2024-12-08 | 100% | Chandraharsha Kosuri
13 | 03. Booking Management | 4.01 | Process Payments | Implement GUI for Displaying Payment Details. | N | 2024-11-24 | 2024-11-30 | 100% | Jitendra Rawat
14 | 04. Payments and Ratings | 4.01 | Process Payments | Implement Error Handling for Payment Failures. | Y | 2024-11-24 | 2024-11-28 | 100% | Jitendra Rawat
15 | 04. Payments and Ratings | 4.01 | Process Payments | Generate and Display Payment Confirmation Summary. | Y | 2024-11-24 | 2024-11-30 | 100% | Jitendra Rawat
16 | 04. Payments and Ratings | 4.01 | Process Payments | Implement Validation for Payment Information. | N | 2024-11-24 | 2024-11-28 | 100% | Prithvi Karkera
17 | 04. Payments and Ratings | 4.01 | Process Payments | Implement Alerts for Failed Transactions. | N | 2024-11-24 | 2024-11-28 | 100% | Prithvi Karkera
18 | 04. Payments and Ratings | 4.01 | Process Payments | Validation for payment information. | N | 2024-11-24 | 2024-11-28 | 100% | Bhavin Goswami
19 | 04. Payments and Ratings | 4.01 | Process Payments | Build API to fetch payment amount. (Calculations) | N | 2024-11-24 | 2024-11-28 | 100% | Jitendra Rawat
20 | 04. Payments and Ratings | 4.01 | Process Payments | Produce Test Design Specification | N | 2024-12-04 | 2024-12-08 | 100% | Bhavin Goswami
21 | 04. Payments and Ratings | 4.01 | Process Payments | Produce Test Case Specification | N | 2024-12-04 | 2024-12-08 | 100% | Charitha Gangaraju
22 | 04. Payments and Ratings | 4.01 | Process Payments | Perform Testing | N | 2024-11-28 | 2024-12-08 | 100% | Krupali Dangshiya
23 | 04. Payments and Ratings | 4.02 | View Payment History | Search for Proper UI Design | Y | 2024-11-24 | 2024-12-09 | 100% | Tarjanee Desai
24 | 04. Payments and Ratings | 4.02 | View Payment History | Identify data fields required for payment history (e.g., date, amount, status, booking ID) | Y | 2024-11-24 | 2024-11-28 | 100% | Prithvi Karkera
25 | 04. Payments and Ratings | 4.02 | View Payment History | Create API endpoints for retrieving payment history. | N | 2024-11-24 | 2024-11-28 | 100% | Prithvi Karkera
26 | 04. Payments and Ratings | 4.02 | View Payment History | Display appropriate messages for no payment records. | N | 2024-11-24 | 2024-11-30 | 100% | Prithvi Karkera
27 | 04. Payments and Ratings | 4.02 | View Payment History | Test that unauthorized users cannot access payment history. | N | 2024-11-24 | 2024-11-30 | 100% | Prithvi Karkera
28 | 04. Payments and Ratings | 4.02 | View Payment History | Produce Test Design Specification | N | 2024-12-04 | 2024-12-08 | 100% | Jitendra Rawat
29 | 04. Payments and Ratings | 4.02 | View Payment History | Produce Test Case Specification | N | 2024-12-04 | 2024-12-08 | 100% | Tarjanee Desai
30 | 04. Payments and Ratings | 4.02 | View Payment History | Perform Testing on Payment History Functionality | N | 2024-11-28 | 2024-12-08 | 100% | Sameera Shaikh
31 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Search for Proper UI Design | N | 2024-12-04 | 2024-12-07 | 100% | Tarjanee Desai
32 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Implement a star-based rating UI and review input field. | Y | 2024-12-04 | 2024-12-07 | 100% | Prithvi Karkera
33 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Validate input fields for ratings and reviews. | N | 2024-12-04 | 2024-12-07 | 100% | Prithvi Karkera
34 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Build API for posting ratings and reviews. | N | 2024-12-04 | 2024-12-07 | 100% | Jitendra Rawat
35 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Generate confirmation message upon successful posting. | N | 2024-12-04 | 2024-12-07 | 100% | Prithvi Karkera
36 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Implement error handling for failed submissions. | N | 2024-12-04 | 2024-12-07 | 100% | Prithvi Karkera
37 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Produce Test Design Specification | N | 2024-12-04 | 2024-12-08 | 100% | Sameera Shaikh
38 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Produce Test Case Specification | N | 2024-12-04 | 2024-12-08 | 100% | Harsh Patel
39 | 04. Payments and Ratings | 4.03 | Post Rating/Review | Perform Testing on post rating functionality | N | 2024-12-06 | 2024-12-09 | 100% | Krupali Dangshiya
40 | 04. Payments and Ratings | 4.04 | View Ratings | Design UI to display average ratings and user reviews. | N | 2024-12-11 | 2024-12-13 | 100% | Tarjanee Desai
41 | 04. Payments and Ratings | 4.04 | View Ratings | Create API endpoints to fetch ratings and reviews data. | N | 2024-12-11 | 2024-12-13 | 100% | Jitendra Rawat
42 | 04. Payments and Ratings | 4.04 | View Ratings | Implement pagination for displaying multiple reviews. | Y | 2024-12-11 | 2024-12-13 | 100% | Charitha Gangaraju
43 | 04. Payments and Ratings | 4.04 | View Ratings | Implement sorting (e.g., newest, highest, lowest rating). | Y | 2024-12-11 | 2024-12-13 | 100% | Jitendra Rawat
44 | 04. Payments and Ratings | 4.04 | View Ratings | Add filtering functionality (e.g., based on rating). | Y | 2024-12-11 | 2024-12-13 | 100% | Jitendra Rawat
45 | 04. Payments and Ratings | 4.04 | View Ratings | Validate data integrity and ensure accurate display. | N | 2024-12-11 | 2024-12-13 | 100% | Bhavin Goswami
46 | 04. Payments and Ratings | 4.04 | View Ratings | Produce Test Design Specification | N | 2024-12-04 | 2024-12-08 | 100% | Krupali Dangshiya
47 | 04. Payments and Ratings | 4.04 | View Ratings | Produce Test Case Specification | N | 2024-12-04 | 2024-12-08 | 100% | Prithvi Karkera
48 | 04. Payments and Ratings | 4.04 | View Ratings | Perform Testing on rating display. | N | 2024-12-11 | 2024-12-14 | 100% | Avinash Bhavancheekar